## Admin
|  | Project: | Multi Vendor eCommerce Websites | Team: | Dev_Team
ADMIN CONTROL PANEL
TASK | Nguyen Tri Quang | Giang Tan Phuc | Vo Khanh Loc | Dang Van Tue | Tran Phuc Tuyen
User Management
1. Code Role Entity, Role Repository and Unit Test , User Listing Function | 1
2. Code New User Function, Encode User Password, Check Uniqueness of User Email - Update User - Update User Enabled Status | 1
3. Code User Photos Upload Function - Pagination, Sorting, Filter Function for Users List. Code Export Users to Excel, PDF, CSV. | 1
User Authentication
1. Code User Login Page + User Authentication | 1
2. Code Logout Function - Show User's Full Name and Logout Link | 1
3. Enabled Remember Me For Login - Code Update Account Details | 1
Show Custom Error Pages And Configure Logging |  |  |  | 1
Category Management Module
1. Code Category Entity and Repository + Unit Tests |  |  | 1
2. Code for Listing Categories + Create Category Function |  |  | 1
3. Check Uniqueness of Category + Update Categoty Function |  |  | 1
4. Code Sort, Pagination, Filter Function for Category List |  |  | 1
5. Code Update Category Enabled Status + Delete Category Function |  |  | 1
6. Code Export Category to CSV |  |  | 1
Code Brand Management Module
1. Code Brand Entity and Repository + Code Listing Brand |  | 1
2. Code Brand Form + Code Category Selection in Brand Form |  | 1
3. Code Create, Update and Delete Brand Function + Check Uniqueness of Brand + Code Pagination, Sort and Filter for Brands Listing |  | 1
Code Product Management Module
1. Code Product Entity and Repository + Unit Tests | 1
2. Code Product Listing Page - Overview Form - Product Form and Shipping | 1
3. Code Save Product Function - Check Uniqueness of Product - Update Product Enabled Status + Code Delete Product | 1
4. Code Upload Product Images - Add + Save Details(Specs) | 1
5. Code Edit - Update - View Product Details in Modal Dialog | 1
6. Code Pagination , Sort and Filter for Products Page | 1
7. Code Filter Products by Category + Authorization for Product Module | 1
Code Settings Module
1. Code Setting, Currency Entity , Repository and Manage General Settings |  |  |  |  | 1
2. Apply General Settings for Shopping Application |  |  |  |  | 1
3. Code Repository Layer for Country and State |  |  |  |  | 1
4. Code Controller Layer for Country + Manage Countries |  |  |  |  | 1
5. Code Manage States/Provinces |  |  |  |  | 1
Code Customer Module
1. Code Edit - Delete Customer + Update Enabled Status + Show Details Customer Modal Dialog |  |  |  | 1
2. Code Pagination, Sort and Filter Customer |  |  |  | 1
Code Contact Module
1. Code Edit - Delete Contact |  |  |  | 1
2. Code Pagination, Sort and Filter Contact |  |  |  | 1
Code Manage Shops
1. Code for Listing Shops and Show Details Modal Dialog |  |  | 1
2. Code Entity and Repository Shop |  |  | 1
3. Code Delete Shop - Update Status Shops |  |  | 1
4. Code Pagination, Sort, Filter Shops |  |  | 1
Code Manage Reviews And Question
1. Code for Listing Review, Question and Show Details Modal Dialog |  |  |  |  | 1
2. Edit - Delete and Update Status Q&A |  |  |  |  | 1
3. Code Pagination, Sort, Filter |  |  |  |  | 1
Code Admin Dashboard
Show Total Users, Categories, Brands, Customer, Shops, Menu, Reviews, Orders, Products, … |  | 1
Manage Articles
1. Code Show Listing Article, Published Status |  | 1
2. Add - Edit - Delete and Show Details Modal Dialog |  | 1
3. Code Pagination, Sort, Filter |  | 1
Manage Menu Items
1. Code Show Listing Menu Items, Update Status |  |  |  |  | 1
2. Code Add - Edit - Delete Function |  |  |  |  | 1
3. Customization Position |  |  |  |  | 1
Manage Sections
Home Page Customization |  |  | 1
Add All Categories Section ¦ Add Product Section ¦ Add Category Section Add Brand Section ¦ Add Article Section ¦ Add Text Section |  |  | 1
Show Listing Section - Code Edit, Delete and Update Enabled Status |  |  | 1
Management Order
1. Code Repository Layer + Order Listing for Order Module | 1
2. Code View Order Details + Delete Order Function | 1
3. Code Edit Order Form (Overview and Shipping) | 1
4. Display Order Tracking Information + Code Edit Product in an Order | 1
5. Calculate Shipping Cost of a Product | 1
6. Code Add Product and Remove to an Orders | 1
7. Code Manage Track Records of an Order | 1
8. Code Save Order into Database - Refactor Code | 1
Code Order Management for Shipper
1. Code Orders Listing for Shipper |  |  | 1
2. Code Service and Controller for Updating Order Status |  |  | 1
3. Code View Layer for Updating Order Status |  |  | 1
Code Manage Sales Report Module
1. Code Repository Layer for Sales Report | 1
2. Code Sales Report by Date - Category - Product | 1
Code Manage Shipping Rates
1. Code Entity Class and Repository Shipping Rates |  |  |  | 1
2. Show Listing Shipping Rates + Update Enabled COD Supported |  |  |  | 1
3. Add - Edit - Delete Shipping Rates |  |  |  | 1
4. Code Pagination, Sort, Filter |  |  |  | 1

## FrontEnd
| Project: | Multi Vendor eCommerce Websites | Team: | Dev_Team
HOME PAGE (StoreFront)
SUMMARY |  | ASSIGNEE | WORKFLOW | NOTE
1. Setup Project |  | Nguyen Tri Quang | COMPLETED
2. Design Database |  |  | COMPLETED | All members
3. Code Home Page for Shopping Application |  | Vo Khanh Loc | COMPLETED
4. Code Listing Categories in Home Page |  | Dang Van Tue | COMPLETED
5. Code Listing Products in Category |  | Tran Phuc Tuyen | COMPLETED
6. Code Product Details Page + Image Slideshow |  | Giang Tan Phuc | COMPLETED
7. Code Search Products Function + Pagination |  | Vo Khanh Loc | COMPLETED
8. Code Customer Registration Form + Manage E-mail Settings |  | Nguyen Tri Quang | COMPLETED
9. Code Send Verification Email + Verify Customer Account |  | Nguyen Tri Quang | COMPLETED
10. Code Customer Login + Remember Me and Logout |  | Tran Phuc Tuyen | COMPLETED
11. Contact Page |  | Dang Van Tue | COMPLETED
12. Update Anthentication Type of Customer |  | Nguyen Tri Quang | COMPLETED
13. Code Login with Google + Facebook and Forgot Password Function |  | Nguyen Tri Quang | COMPLETED
14. Code Update Customer's Details |  | Giang Tan Phuc | COMPLETED
15. Code Quantity Control Component + Add Product to Shopping Cart |  | Nguyen Tri Quang | COMPLETED
16. Code View Shopping Cart + Update Product Quantity |  | Nguyen Tri Quang | COMPLETED
17. Code Remove Product from Shopping Cart |  | Tran Phuc Tuyen | COMPLETED
18. Format Currency in Shopping Cart |  | Dang Van Tue | COMPLETED
ADDRESS BOOK MODULE
19. Code Repository Layer for Address Book + Address Book Listing |  | Giang Tan Phuc + Dang Van Tue | COMPLETED
20. Code Add, Edit and Delete Address |  | Giang Tan Phuc + Dang Van Tue | COMPLETED
21. Code Set Default Address |  | Giang Tan Phuc + Dang Van Tue | COMPLETED
CHECKOUT MODULE
22. Update Shopping Cart Page + Checkout Page |  | Nguyen Tri Quang | COMPLETED
23. Shipping Address from Checkout Page + Update Setting Module |  | Nguyen Tri Quang | COMPLETED
24. Code Place Order with COD, Paypal + Send Order Confirmation Email |  | Nguyen Tri Quang | COMPLETED
25. Code Review Voting Module + Question Module |  | Nguyen Tri Quang | COMPLETED
26. Multi Vendor Shop |  | Nguyen Tri Quang | COMPLETED
And More …

## Project Overview
Code Real-life Shopping Website with Java and Spring Boot. Full-stack Development. Hands-on Practices. Job-ready Skills.
Hands-on Practices. Job-ready Skills.
1. Develop a complete shopping website using Java, Spring Boot, Thymeleaf, Bootstrap, jQuery and MySQL database
2. Code the Admin application for managing users, categories, brands, products, customers, orders, sales report...
3. Code the Shopping application allowing customers to browse products and place orders
4.Code shopping cart features and payment via PayPal and credit cards
5.Use Spring Data JPA with Hibernate for the data access layer
6.Use Spring Security for authentication and role-based authorization
7.Use Thymeleaf template engine for creating dynamic view pages
8. Use Bootstrap and jQuery for creating responsive, mobile-friendly web pages
9. Use Spring RESTful Webservices in conjunction with jQuery on the client side
10. Use PayPal Checkout API for payment integration
11. Use JUnit, Spring Test, AssertJ and Mockito for unit tests and integration tests
12. Deploy the application on Heroku cloud platform with file upload on Amazon S3
13.Use Google Chart for drawing charts in sales report
14. Use Spring OAuth for single sign on with Facebook and Google
15. Use Spring Mail for sending emails for customer registration and place order confirmation
Notes
No. | URL / IP | User | Password
1. Admin | http://localhost:8080/Admin/ | admin@gmail.com | 12345678
2. Client | http://localhost:80/Client/
Notes